UNITED NATIONS CAPITAL DEVELOPMENT FUND (UNCDF)

Kigoma Joint Program on Agriculture: Scaling Up access to Finance in the Kigoma Region

REQUEST FOR APPLICATIONS (RFA)

# UNCDF Financial Inclusion Practice Area

Location: Dar-es-Salaam and the Kigoma Region, Tanzania

Objective: UNCDF is looking for a partner who will deploy a technology-based solution built on an existing digital platform to collect and aggregate smallholder farmer data that can be leveraged for data-driven decision-making for financial services.

Timeline:

•	Publication date: Feb 14, 2019

•	Final deadline for applications: March 3, 2019

Expected duration of Assignment: up to 1 year with possibility of renewal

Language required: English, Kiswahili

Applications should be returned to the UNCDF by email at fipa.procurement.tz@uncdf.org no later than midnight on Feb 14, 2019 East Africa Time (EAT).

Applications must follow the submission format as outlined in Annex 1 of this RfA. Note that submissions to this address may not exceed 10MB. If size of the application is an issue, a DropBox or Google Drive link is acceptable.

Annex 1 is the Submission Format

Annex 2 is a Sample of UNCDF Language Regarding Proprietary Rights of Knowledge Products

- ORGANIZATIONAL CONTEXT AND BACKGROUND INFORMATION

UNCDF makes public and private finance work for the poor in the world’s 47 least developed countries (LDCs). With its capital mandate and instruments, UNCDF offers “last mile” finance models that unlock public and private resources, especially at the domestic level, to reduce poverty and support local economic development. This last mile is where available resources for development are scarcest; where market failures are most pronounced; and where benefits from national growth tend to leave people excluded.

UNCDF’s financing models work through two channels: savings-led financial inclusion that expands the opportunities for individuals, households, and small businesses to participate in the local economy, providing them with the tools they need to climb out of poverty and manage their financial lives; and by showing how localized investments — through fiscal decentralization, innovative municipal finance, and structured project finance — can drive public and private funding that underpins local economic expansion and sustainable development. UNCDF financing models are applied in thematic areas where addressing barriers to finance at the local level can have a transformational effect for poor and excluded people and communities.

By strengthening how finance works for poor people at the household, small enterprise, and local infrastructure levels, UNCDF contributes to SDG 1 on eradicating poverty with a focus on reaching the last mile and addressing exclusion and inequalities of access. At the same time, UNCDF deploys its capital finance mandate in line with SDG 17 on the means of implementation, to unlock public and private finance for the poor at the local level. By identifying those market segments where innovative financing models can have transformational impact in helping to reach the last mile, UNCDF contributes to a number of different SDGs and currently to 28 of 169 targets.  More information can be found on UNCDF here:

UNCDF in Tanzania:

In Tanzania, UNCDF is part of the broader Kigoma Joint Programme (KJP), working with WFP, FAO, and ITC to increase the income of smallholder farmers in the Kigoma region, leading to agricultural and economic development in the region. Using a value chain approach, the program addresses the various bottlenecks in the maize, beans and cassava value chains to increase the investment from smallholder farmers in agriculture, while lowering the associated risk of such investments and increasing private sector engagement. To pave the way for increases in productivity, income, profitability and improved livelihoods, UNCDF is deepening access to finance for the smallholder farmers by strengthening savings and loan groups, linking farmers to financial service providers while building their financial capability and business skills.

2. 	OBJECTIVE OF THE CURRENT PROJECT AND RFA

2.1.	The Kigoma Joint Programme (KJP)

The Kigoma region has experienced a relative increase in poverty levels, and it is also the region that hosts most of the refugees in Tanzania.  Launched in September 2017, the Kigoma Joint Programme (KJP) is an area-based UN joint programme that cuts across multiple sectors to improve development and human security in Kigoma. The Kigoma Joint Programme applies a comprehensive approach to address a wide range of issues facing both the refugees in the region as well as the surrounding host communities.

The humanitarian-development nexus is supported by linking together the UN’s existing response to refugees and migrants with an increased focus on developing the host communities. 16 participating UN agencies are cooperating across 6 themes which include sustainable energy and environment; youth and women’s economic empowerment; violence against women and children; education with a focus on girls and adolescent girls; WASH (Water, Sanitation and Hygiene) and agriculture with a focus on developing local markets.

Under the agricultural theme of the KJP, UNCDF works with WFP, FAO and ITC to grow the capacity of smallholder farmers in order to increase farm income and support the fight against the effects of climate change. Farmers will also gain improved knowledge on post-harvest handling of crops and how to access markets and finance for their goods leading to agricultural development in the region and eventually expand opportunities which would also reduce poverty and vulnerabilities.

UNCDF is working to strengthen farmer groups, promote financial inclusion and access to financial products and services that can improve farmer outputs and increase farm income, and build farmers’ financial capability.

Access to financial services, information and market are key challenges faced by farmers.  Digital services have the potential to address these three factors in a cost effective and affordable manner. The programme expects to reach 15,000 smallholder farmers with access to finance for input needs and products to reduce post-harvest losses. Through stronger savings groups, access to knowledge on agricultural best practices interwoven with financial and digital literacy education and access to finance, UNCDF intends to help smallholder farmers reach their potential with increased yields, better quality products and access to markets.

2.2 	UNCDF’s Request for Applications (RFA)

UNCDF seeks to identify and support the scale-up of innovative digital financial solutions that could make use of micro-savings as well as geographical and agricultural production data to offer financial access alternatives for smallholder farmers.

The purpose of this RfA is to recruit a firm to work in partnership with UNCDF to deploy a technology-based solution built on an existing digital platform to collect and aggregate smallholder farmer data that can be leveraged for data-driven decision-making for financial services.

The expected result is that UNCDF will partner with one of the shortlisted organizations to 1) determine data points to be collected to achieve project objectives, 2) collect and clean farmer data and establish a system for regular data collection and validation, 3) analyze data and provide insights on farmer cash/crop cycle, 4)  facilitate access to finance for farmers, 5) identify additional uses of data for farmers in their crop marketing and planning cycle 6) enhance monitoring and evaluation of programme through data analytics.

Applicants will be evaluated based on:

- expertise and experience in collecting, aggregating and mining data for agricultural use;

- cost-effectiveness and sustainability of the proposed approach;

- potential for scale of the proposed approach;

- operations in Tanzania with experience working in rural regions;

- experience working with government stakeholders at local and national level, smallholder farmers and financial service providers.

2.3.	Timing

Applications should be returned to UNCDF Tanzania by email, no later than midnight on March 3, 2019 East Africa Time (EAT). It is anticipated that the shortlisting will be completed within 2 weeks of application submission. The time needed for submission of revised proposals, if necessary, will depend on the thoroughness and complexity of initial proposals but should take no more than 2 weeks. UNCDF aims to conclude all agreements no later than 15 April 2019.

The expected duration of the assignment is 1 year with option for renewal; the expected date of full completion is 30 June 2020. Further collaboration may be sought contingent upon performance and funding. The applicant(s) should propose a timeline and work plan for their own proposed project.

2.4.	Contact

- Applications and any consultation about this RFA should be submitted via email at:

Fipa.procurement.tz@uncdf.org

- The subject line of the email should be:  RFA KJP: Scaling Up Access to Finance in the Kigoma Region

2.4.	Responses

All queries and submitted applications will be acknowledged.

3. 	SCOPE OF WORK

UNCDF Tanzania seeks a firm or organization to partner with in Kigoma to deploy a technology-based solution built on an existing digital platform to collect and aggregate smallholder farmer data that can be leveraged for data-driven decision-making for financial services.  Under this Scope of Work, the grantee will perform the following activities and be responsible for the delivering the following outputs:

3.1.	Expected Activities and Outputs

    - Collect, clean and keep updated existing project database of 5,000 farmers.

KJ-P partner agencies have collected and digitized data on 5,000 smallholder farmers organized into 200 farmer groups. However, this data needs to be validated to allow integration into the selected firm’s platform. The firm will then be responsible for updating and ensuring that data remains current on a regular basis.  Data includes value chain data as well as individual farmer and group data.

Outputs:

- Validated data of existing farmers.

- List of useful data to be collected on a regular basis.

- Continual data collection systems designed and tested.

    - Design farmer training and informational sessions on data collection platform.

Outputs:

- Farmer training guide and training delivery proposal.

- 200 farmer groups informed/trained on data platform, benefits and client protection measures.

- Local gov’t authorities trained and informed about data platform.

    - Design project-related dashboards for the following uses:  1) monitoring and evaluation; 2) facilitating access to finance; 3) marketing and crop production planning.

Outputs:

- Three dashboard templates tested and finalized.

- Business case developed for FSPs to reach new client base, reduce risk and improve portfolio monitoring.

- If necessary, government approvals and/or no-objection received.

    - Support UNCDF’s discussion with input providers and financial service providers to adapt and pilot product delivery to farmer groups.

Outputs:

- Farmer database allows for service provider integration.

- Data based solution for access to finance piloted with at least 1 FSP.

- Identify FSP capacities that need strengthening to leverage data analytics.

    - Coordination, monitoring and reporting on data-related activities.

Outputs:

- Regular contact with local stakeholders

- Monthly reporting to UNCDF – narrative and quantitative

- Participate in regional workshops to share lessons learned and good practice.

    - Support with scale-up and next-phase of agricultural data analytic solutions.

Outputs:

- Proposed expansion plan

- Brief on lessons learned

4.	 AGREEMENT PARAMETERS

4.1. 	Outputs and deliverables

The written and technological outputs and deliverables of the work are considered a public good unless otherwise agreed. Thus, all the outputs and deliverables will be placed in the public domain with the intent that they can and should be freely and widely used by other parties.

4.2.	Agreement

The technical partner is expected to sign a Performance Based Financing (Grant) Agreement with UNCDF by April 15, 2019 (Applicants not familiar with UNCDF agreements are encouraged to request a sample from fipa.procurement.tz@uncdf.org prior to submission of application).

4.3.	Language

The deliverables, as well as any and all related correspondence exchanged by the organization and UNCDF, shall be written in English.  English and Kiswahili will be used for the technical tools and documents to be used in reaching beneficiaries.

4.4. 	Global Access and Intellectual Property

Public good: The outputs produced will have the consideration of public good. In line with the public good nature of the grant, UNCDF may place all the deliverables specified in the public domain with the intent that they can and should be freely and widely used by other parties and the RECIPIENT INSTITUTION shall not be excluded from the ability to use such deliverables on the same basis as other external parties. The RECIPIENT INSTITUTION sign and accept the legal language in Annex 2, without modification, of the UNCDF grant agreement (performance based). UNCDF also has the right to assign custody of this public good to a public authority as appropriate

5.  ELIGIBILITY REQUIREMENTS AND EVALUATION CRITERIA

5.1. 	Minimum qualification criteria

- Any type of organization (commercial for-profit firms, educational institutions, and non-profit organizations, Universities) operating a digital platform specialized in data

- Currently operating in Tanzania

- Demonstrated forged partnerships with at least one mainstream financial service provider.

- Successfully conducted similar assignments at a country or regional level with proven results. Involvement in similar program(s) that are currently running would be an advantage.

- Demonstrated relevant experience and capability of proposed staff members.

- Duly registered and operating in compliance with Tanzania’s laws and regulations.

- Ability to work in English and Kiswahili.

- Flexibility in adopting products and services to local contexts to fit the needs of smallholder farmers as well as for women and youth.

- Submission of a complete application.

  - Other requirements and qualifications

- Experience working with local government at ward, district, regional and national levels.

- Experience working with financial service providers, mobile network operations, community-based organizations, and understanding of the challenges of working with them.

- Commitment and ability to provide on-site resources (e.g. staff, consultants) as needed.

- Extensive experience training trainers and providing participative trainings.

- APPLICATION REQUIREMENTS

6.1 Structure of the Application

- The application includes a suggested template for submissions in Annex 1: Submission Format.

Additional documents or links to documents may be included at the applicant’s discretion. Please consider that UNCDF email accounts are only able to receive attachments of up to 10MB and links to larger files are often preferable.  If size of the application is an issue, a DropBox or Google Drive link is acceptable.

6.2   Technical proposal:

The technical proposal shall be structured as follows:

- Methodology and approach to achieve the objectives of the project

- Detailed work plan with timeline of major activities

- Overview of past examples of similar projects, including references

- Proposed team (with CVs in Annex)

  - Financial proposal:

The submission must include a budget quotation for the project based on activities and outputs listed in section 3.1 with estimated implementation time of 1 year (see Annex 1, section 5). The financial proposal must provide a detailed breakdown of costs. Please provide separate figures for each functional grouping or category.

6.4 Submission of the Application

- Applications and any consultation about this RFA should be submitted via email at fipa.procurement.tz@uncdf.org

- The subject line of the email should be:  RFA KJP: Scaling Up Access to Finance in the Kigoma Region

- The deadline to submit the application is 3 March 2019 at midnight EAT

ANNEX 1: SUBMISSION FORMAT

[insert: Location]

[insert: Date

To:	Ivana Damjanov, Technical Specialist, UNCDF Tanzania

Dear Madam:

We, the undersigned, hereby apply for   Kigoma Joint Program on Agriculture: Scaling Up access to Finance in the Kigoma Region in accordance with your Request for Application dated 2/14/2019 and our Application.  We are hereby submitting our Application, which includes the Technical Proposal and Financial Proposal.

We hereby declare that:

- All the information and statements made in this Application are true and we accept that any misrepresentation contained in it may lead to our disqualification; and

- We have no outstanding bankruptcy or pending litigation or any legal action that could impair our operation as a going concern.

We confirm that we have read, understood and hereby accept the duties and responsibilities required of us in this RFA, and the standard language of UNCDF’s Performance Based Agreements (PBA), including the requirements regarding the public good nature of the outputs to be produced (see Annex 2 for a sample of our legal language in this regard). Therefore, if our application is accepted, we will be ready to sign and accept the legal language, without modification, of the UNCDF grant agreement (performance based) by XXX.

We fully understand and recognize that UNCDF is not bound to accept this application, that we shall bear all costs associated with its preparation and submission, and that UNCDF will in no case be responsible or liable for those costs, regardless of the conduct or outcome of the evaluation.

We remain,

Yours sincerely,

Authorized Signature [In full and initials]:

Name and Title of Signatory:

Name of Firm:

Contact Details :

[please mark this letter with your corporate seal, if available]

Page ________of ________ pages

| SECTION 1: GENERAL APPLICANT’S INFORMATION |  |  |
| --- | --- | --- |
| 1. Applicant’s Legal Name: |  |  |
| 2. Type of Organization (e.g. commercial for profit firm, educational, non-profit etc): |  |  |
| 3. In case of Joint Venture (JV), legal name of each party: |  |  |
| 4. Actual or intended Country/ies of Registration/Operation: |  |  |
| 5. Year of Registration: |  |  |
| 6. Countries of Operation | 7. No. of staff in each Country | 8.Years of Operation in each Country |
| 9. Legal Address/es in Country/ies of Registration/Operation: |  |  |
| 10. Value and Description of Top three (3) Grants or Contracts relevant to the scope of this RFA for the past five (5) years: Name of the project: Client/Funder (if applicable): Grant/Contract value: Types of Results Produced/activities undertaken: References, contact details: |  |  |
| 11. Latest Credit Rating (if any) |  |  |
| 12. Brief description of litigation history (disputes, arbitration, claims, etc.), indicating current status and outcomes, if already resolved. |  |  |
| 13. Applicant’s Authorized Representative Information Name: Address: Telephone/Fax numbers: Email Address: |  |  |
| 14. Are you in the UN Ineligibility List? ☐ YES or ☐ NO |  |  |
| 15. Attached are copies of original documents of: ☐ Audited financial statements for the past 2 years duly certified by a public accountant ☐Letter from the applicant organization’s executive director, CEO, or board, expressing its commitment to the execution and participation in this process. ☐Complete CVs of all the team members involved in the assignment ☐ Staff time allocation spreadsheet per activity ☐Evidence of similar applications produced under similar assignments (this can be links in a website, for example). |  |  |
| SECTION 2: SPECIFIC EXPERIENCE FOR THE ASSIGNEMENT. |  |  |
| 2.1. Please describe your organization’s experience in producing similar projects. For each, make sure you describe the following (maximum 2 pages per project): Name of the project: Client/Funder (if applicable): Grant/Contract value: Dates and location of the project: Description of the approach/methodology: Types of outputs produced/activities undertaken: Tools used or developed (dashboards, maps, etc.): Project results (if known): Time it took you to complete the assignment: Number of people and names of the staff that participated in the assignment: Knowledge product production and dissemination strategy of the assignment; References, contact details: |  |  |
| 2.2. Please describe your organization’s experience in understanding the needs of the target groups outlined in Section 3 of this RFA (refugees, rural populations, women, youth). (Maximum 2 pages) |  |  |
| 2.3. Please describe your organization’s experience in developing creative technology-based applications that focus on behavior change (maximum 1 page) |  |  |
| 2.4. Please describe your organization’s experience in Tanzania, rural areas, or similar contexts (maximum 1 page) |  |  |
| SECTION 3: APPROACH AND IMPLEMENTATION PLAN (maximum 10 pages) |  |  |
| 3.1. Approach to the Results Required: Please provide a detailed description of the methodology for how the organisation/firm will achieve project outputs, keeping in mind the appropriateness to local conditions and project environment. 3.2. Approach to Partnership with UNCDF and field-based Partners: The applicant must provide a detailed description of the applicant will plan, implement and deliver the overall project in partnership with UNCDF and field-based partners. The applicant should describe how they will take the lead role in ensuring that there is sufficient and ongoing communication, both virtually and in person. This section should highlight the support necessary from UNCDF and local partners. 3.3. Technical Quality Assurance Review Mechanisms: The methodology shall also include details of the applicant’s internal technical and quality assurance review mechanisms. 3.4 Implementation Timelines: The Applicant shall submit a Gantt Chart or Project Schedule indicating the detailed sequence of activities that will be undertaken and their corresponding timing, specifying timelines, person responsible, and time devoted to each activity. 3.5. Sub-grantees: Explain whether any work would be delegated, to whom, how much percentage of the work, the rationale for such, and the roles of the proposed sub-grantees. Special attention should be given to providing a clear picture of the role of each entity and how everyone will function as a team. 3.6. Risks / Mitigation Measures: Please describe the potential risks for the implementation of this project that may impact achievement and timely completion of expected results as well as their quality. Describe measures that will be put in place to mitigate these risks. Given the sensitivity of refugee data, the applicant should consult and consider and address issues around data privacy and security specifically for this group. 3.7. Reporting and Monitoring: Please provide a brief description of the mechanisms proposed for this project for reporting to (and ongoing communication with) UNCDF and partners, including a reporting schedule (also reflected in Gantt chart). 3.8 Other: Any other comments or information regarding the project approach and methodology that will be adopted. |  |  |
| SECTION 4: PERSONNEL |  |  |
| 4.1 Management Structure: Describe the overall management approach toward planning and implementing this activity. Include an organization chart for the management of the project describing the relationship of key positions and designations along with information on the roles and structure of any sub-grantees, contractors, or other critical relationships. 4.2 Staff Time Allocation: Provide a spreadsheet to show the activities of each staff member and the time allocated for his/her involvement. (Note :This spreadsheet is crucial and no substitution of personnel will be tolerated once the grant has been awarded except in extreme circumstances and with the written approval of UNCDF. If substitution is unavoidable it will be with a person who, in the opinion of the UNCDF, is at least as experienced as the person being replaced, and subject to the approval of UNCDF. No increase in costs will be considered as a result of any substitution.) 4.3 Qualifications of Key Personnel. Provide the CVs for key personnel (Team Leader, Managerial and general staff) that will be provided to support the implementation of this project. CVs should demonstrate qualifications in areas relevant to the results to be produced. In addition to the CVs, please submit a summary for each person in the following format: Name:. Position for this Contract:. Nationality:. Contact information:. Countries of Work Experience:. Language Skills:. Educational and other Qualifications:. Summary of Experience: Highlight experience in the region and on similar projects.. Relevant Experience (From most recent):. Period: From – To; Name of activity/ Project/ funding organisation, if applicable:; Job Title and Activities undertaken/Description of actual role performed:. e.g. June 2004-January 2005. Etc.. Etc.. Reference no.1 (minimum of 3):; Name Designation Organization Contact Information – Address; Phone; Email; etc.. Reference no.2; Name Designation Organization Contact Information – Address; Phone; Email; etc.. Reference no.3; Name Designation Organization Contact Information – Address; Phone; Email; etc.. Declaration: I confirm my intention to serve in the stated position and present availability to serve for the term of the proposed grant agreement. I also understand that any wilful misstatement described above may lead to my disqualification, before or during my engagement. _________________________________________________ __________________________ Signature of the Nominated Team Leader/Member Date Signed. |
| SECTION 5: BUDGET PROPOSAL |  |  |
| Please provide budget allocation in the following suggested or similar format: - Summary of costs Level of effort; # Days; Cost; Total. Team member #1; .. days. Team member #2; .. days. …..; .. days. Sub-Total LOE; USD …. Travel/mission/other budget; Cost; Total. Travel. Equipment / Technology. Consultants / sub-grantees. Other (describe). Sub-Total Travel. Total; USD …. |

ANNEX 2: SAMPLE OF UNCDF LANGUAGE REGARDING PROPRIETARY RIGHTS OF KNOWELDGE PRODUCTS PRODUCED UNDER THIS ASSIGNMENT

6.0	COPYRIGHT, PATENTS AND OTHER PROPRIETARY RIGHTS:

6.1	Except as is otherwise expressly provided in writing in the Agreement, the UNCDF shall be entitled to all intellectual property and other proprietary rights including, but not limited to, patents, copyrights, and trademarks, with regard to products, processes, inventions, ideas, know-how, or documents and other materials which the RECIPIENT INSTITUTION has developed for the UNCDF under the Agreement and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Agreement, and the RECIPIENT INSTITUTION acknowledges and agrees that such products, documents and other materials constitute works made for the UNCDF. In line with the public good nature of the grant, UNCDF will place all the deliverables specified in the public domain with the intent that they can and should be freely and widely used by other parties and the RECIPIENT INSTITUTION shall not be excluded from the ability to use such deliverables on the same basis as other external parties.

6.2	To the extent that any such intellectual property or other proprietary rights consist of any intellectual property or other proprietary rights of the Recipient Institution: (i) that pre-existed the performance by the Recipient Institution of its obligations under the Agreement, or (ii) that the Recipient Institution may develop or acquire, or may have developed or acquired, independently of the performance of its obligations under the Agreement, the UNCDF does not and shall not claim any ownership interest thereto, and the Recipient Institution grants to the UNCDF a perpetual license to use such intellectual property or other proprietary right solely for the purposes of and in accordance with the requirements of the Agreement.

6.3	At the request of the UNCDF; the Recipient Institution shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring or licensing them to the UNCDF in compliance with the requirements of the applicable law and of the Agreement.

6.4	Subject to the foregoing provisions, all maps, drawings, recordings, transcriptions, photographs, mosaics, plans, reports, estimates, recommendations, documents, and any and all other data compiled by or received by the Recipient Institution under the Agreement shall be the property of the UNCDF, shall be made available for use or inspection by the UNCDF at reasonable times and in reasonable places, shall be treated as confidential, and shall be delivered only to UNCDF authorized officials on completion of work under the Agreement.