UNITED NATIONS CAPITAL DEVELOPMENT FUND (UNCDF)

Boosting Green Employment and Enterprise Opportunities In Ghana

Development and management of a crowdfunding platform: pilot phase

Request for application (RfA)

Deadline for submissions: April 30th , 2020 at 1pm GMT+0

- Description of project

The United Nations Capital Development Fund (UNCDF) makes public and private finance work for the poor in the world’s 47 least developed countries. With its capital mandate and instruments, UNCDF offers “last mile” finance models that unlock public and private resources, especially at the domestic level, to reduce poverty and support local economic development. UNCDF’s financing models work through three channels: inclusive digital economies, connecting individuals, households, and small businesses with financial eco-systems that catalyze participation in the local economy, and provide tools to climb out of poverty and manage financial lives; local development finance, that capacitates localities through fiscal decentralization, innovative municipal finance, and structured project finance to drive local economic expansion and sustainable development; and investment finance, that provides catalytic financial structuring, de-risking, and capital deployment to drive SDG impact and domestic resource mobilization. By strengthening how finance works for poor people at the household, small enterprise, and local infrastructure levels, UNCDF contributes to Sustainable Development Goal-SDG 1 on eradicating poverty and SDG 17 on the means of implementation. By identifying those market segments where innovative financing models can have transformational impact in helping to reach the last mile and address exclusion and inequalities of access, UNCDF contributes to a broad diversity of SDGs.

UNCDF is bringing its expertise in promoting financial inclusion to support job creation for youth “Boosting  Green Employment and Enterprise Opportunities in Ghana (GrEEn)” programme to be funded by the European Union Trust Fund for Africa. This programme will contribute to addressing the root causes of irregular migration through green and climate resilient local economic development and improving future prospects of beneficiaries, by creating employment and enterprise opportunities in selected sectors and regions (Ashanti and Western). The action aims at supporting job creation in regions of departure, transit and return of Ghana, creating local financial ecosystems that facilitate the development of Micro, Small and Medium Enterprises (MSMEs) and enabling the transition of local economies to green and climate resilient development. The programme will use the lessons learnt from UNCDF experience in (i) Performance-Based Climate Resilience Grants (PBCRGs) which support investments for green and resilient local economies across 13 countries as well as (ii) best practices to advance increase access to finance for youth and digital finance. The action will be implemented in conjunction with SNV using their model for youth entrepreneurs ‘Opportunities for Youth Employment (OYE) programme’, SNV’s most advanced multi-country programme thus far, which targeted 27,000 rural out of school youth in Tanzania, Rwanda and Mozambique.

The main results under the UNCDF-EUTF agreement are the following:

- Result 1 (R1): Local economies are stimulated through green and climate resilient investments executed through cash for work modalities and/or procurement to local SMEs and therefore creating short-term job opportunities for youth, women and returnees . The first set of activities under Results 1 will aim at informing and participatory planning to help MMDAs and communities to identify and select local resilient investments to be financed by the PBCRGs and by the diaspora through a crowdfunding platform to be developed under Results 3. MMDAs will benefit from assistance to undertake or utilise risk assessment and establish local information systems for risk informed planning, in partnership with universities and research institutes. Awareness and sensitization activities will be undertaken. Needs and capacity gaps will be assessed and addressed through targeted capacity building activities.

- Result 2 (R2): Employability of youth, women and returnees are improved through orientation support and assistance, so that they can benefit from the cash for work opportunities created in Result 1. Coordination and synergies will be ensured with the activities undertaken by UNCDF joint Programme partner SNV for broader activities under Result 2 and Result 4 “SMEs, offering decent and sustainable jobs to youth, women and returnees, are incubated and/or accelerated and contribute to green and climate resilient local economies”.

- Result 3 (R3): Increased access and usage of financial services, leveraging remittances and digital solutions, adapted to the needs of (i) youth, women and returnees benefiting from cash for work schemes and (ii) local communities and MSMEs. The third set of activities under Results 3 will facilitate access and usage of targeted beneficiaries (youth, women, returnees, MSMEs) to financial services. The action will focus on the Diaspora and will leverage it to advance financial inclusion of Ghana’s most vulnerable groups.  In particular, the activities under R3 will aim to build financial capabilities of clients; support the supply-side to provide financial services adapted to the target’s needs as well as test and pilot innovative financial solutions (e.g. crowdfunding) to better channels investments at the local level.

Under Result 3 (access to finance), UNCDF wants to test and/or scale up innovative financial services: innovation to accelerate the process of asset accumulation and access to finance for the creation/expansion of economic opportunities for the beneficiaries is at the core of UNCDF’s strategy for this action. Moreover, within the recent COVID 19 outbreak that has challenged the world in an unprecedented manner, financial inclusion and Digital Financial Services (DFS) are seen as solutions to support the initial response and economic recovery of countries affected by the COVD-19 pandemic. Financially included people are better prepared to manage cash flow and mitigate risks, and thus more likely to be economically resilient.

Crowdfunding and Peer-to-peer lending platforms, in particular, offer alternative financing options for youth entrepreneurs’ access to seed capital now more than ever. With many young entrepreneurs looking to family and friends for start-up funds for their businesses, crowdfunding offers the possibility of pooling these funds in a formal structure and building a financial history which will allow FSPs to better engage these entrepreneurs. Within the COVID responses, crowdfunding solutions could support innovations developed by local young entrepreneurs to fight COVID-19.

While international crowdfunding platforms are abundant, they do not seem targeted to specific country context: just to name a few,  payment systems available on international platforms restrict contributions originating in lower-income countries or do not detect informal flows at the household level, for example. Internal research shows that existing solution do not often include training and country-specific marketing strategies to ensure uptake and usage of disadvantaged segments. Also, when it comes to pay out the campaigners, international platforms do not have specific linkages with financial services  providers that offer tailored financial services to poor youth, resulting in a vicious cycle of financial exclusion. This is why UNCDF want to test a new integrated approach tailored to the context in Ghana to ensure access and usage of new innovative platform that combines different way of raising funds while giving useful solution to tackle the COVID 19 outbreak.

It is within this context that UNCDF want to test a crowdfunding platform in the Gambia through the Jobs, Skills, and Finance Programme to help young entrepreneurs in their financing endeavors.

- OBJECTIVES OF THE REQUEST FOR APPLICATION (RFA)

The purpose of this RFA is to select qualified technical partners (FinTech, consulting firms, technical providers, non-profit organizations, training providers etc.) committed, ready and able to implement a quick win solution to develop (or adapt) and manage a crowdfunding solution to be offered to targeted beneficiaries in Ashanti and Western regions of Ghana as a way to provide them with source of financing to scale up innovations at local level for their businesses. During the first year of operations, businesses supported that are providing solutions to fight the COVID 19 crisis will receive a priority.

UNCDF is looking for a partner able to:

- Propose a first round of campaigns in a very short term as response to COVID 19 crisis (campaigns can be either for immediate needs as medical supplies as well as funding support to young entrepreneurs with innovative solutions to fight the COVID 19).

- Scout and support young entrepreneurs to start their campaigns and fully own the solution, in collaboration with local hubs. UNCDF can connect the selected partners with local hubs of young entrepreneurs.

- Identify local and international payment solutions that allow both national and international (diaspora) donations or investment.

- Design activities of outreach campaigns to create trust and awareness among potential users and the general public, both in-country and abroad (e.g. e-learning platform).

- Envision incentive scheme (e.g. matching funds) to support young entrepreneurs with innovative solution to fight COVID 19.

- Plan a scale up of the quick win action for a broader response after the COVID-19 emergency as a way to support businesses to cope with economic consequences of the health crisis. In particular:

  - identify key potential financial providers to join the platform and complement the funds raised with additional financial services and matching funds (loans, equity, etc)

  - provide technical assistance to the youth so that they acquire the skills to fully use the potential of the platform (e.g. to “pitch” their business to investors)

  - design a business model to be scaled up and self-sustainable by the end of the project

  - add options to the crowdfunding model, e.g. donations, investment, reward based, etc.

  - help diaspora to channel their investments into local resilient opportunities identified and supported by local governments participating in the programme

The learning questions that UNCDF would like to address with this project are:

| Learning Questions | KPIs |
| --- | --- |
| What is the impact of crowdfunding platforms on vulnerable segments, in particular youth and women, in mobilizing funds? | Financial flows received |
| How does crowdfunding help FSPs in de-risking investing in the youth and women segments? | New clients; default rates of targeted clients |
| What are the complementary non-financial services needed for the crowdfunding platform to be successful for youth and women? | Evaluations, participant surveys |
| What are the sources of funding the youth and the women tap more into when mobilizing the funds from the crowdfunding platform (diaspora or domestic) | Platform MIS, evaluations, participant surveys |
| What are the most effective ways to involve the diaspora? | Evaluations, investors surveys |

- PROJECT IMPLEMENTATION AND DELIVERABLES

Partners are expected to be engaged in the following activities and expected deliverables:

| Main activities | Deliverables |
| --- | --- |
| Stage 1: Market research and Business Plan The partner will conduct market research and develop a business plan for the quick win action. The selected partner will work closely with financial and payment service providers to identify how pays outs and donations/investments will work. During this stage, the partner needs to identify young entrepreneurs that have innovative solutions in response to COVID 19 that lack funding in the targeted regions. | Stage 1: Market research and business plan - Market Research Report - Action plan for the quick win action |
| Stage 2: Prototype development The selected partner will be expected to develop or to adapt their existing platform to the needs of the targeted users. Please make sure you define the crowdfunding model (donation/reward/equity/investment/etc) most suitable for the Ghanaian context and for the RFA objectives. Please make sure you highlight the cost of technology (development), adaptation to the country context (branding, contents development, training modules, etc). | Stage 2: Prototype development - Prototype of the platform for review by UNCDF or transition plan for an existing platform - Branding of the platform and awareness/marketing plans |
| Stage 3: Testing, adaptation and Iteration of the quick win action During this stage, the selected partner could first test the platform with pre identified potential users to help them raise funds for their innovative solution. A first set of marketing activities to make sure the solutions is well advertised among investors (including diaspora). The platform should be compatible to handle at least 1,000 users for the quick win action. | Stage 3: Testing, adaptations and Iteration - Report highlighting the results of the field test and the changes made to the platform - Final Platform Design Brief - Marketing plan and outreach - Lessons learned reports |

According to the partnerships and results achieved, the selected partner may be awarded with additional funding for the scale up, namely:

| Stage 4: Launch, marketing and deployment of the Platform The selected partner will ensure the platform is launched and deployed. The selected partner will also be responsible for marketing of the platform with the returnees, youth and the women, investors in Ghana and outside (Diaspora). The marketing plan should incorporate a region-wide social media campaign in Ashanti and Western region. The platform should be compatible to handle at least 2,000 beneficiaries in its first year and no less than 15,000 beneficiaries in the two selected regions in Ghana after 3 years. Ownership of the platform should be clearly articulated in the proposal along with how the selected partner intends its continuity post-UNCDF granting. | Stage 4: Launch, marketing and deployment of the Platform - Report on platform’s deployment per region in Ghana - Marketing strategy to attract users and investors - Quarterly reports on key metrics on platform usage |
| --- | --- |
| Stage 5: Monitoring, quality assurance of the scale up and supporting learning agenda The selected partner will scale up the platform country wide and will monitor results in line with UNCDF’s learning agenda and should include all relevant information (behavioural data, financial flows) that help project partners to answer the learning questions. | Stage 5: Monitoring, quality assurance and supporting learning agenda - Quarterly reports on key metrics on solution usage segregated by sex, by age, type of business, geography etc. - Case studies on the beneficiaries of the platform |

- AGREEMENT PARAMETERS

Duration: 12 months. The first campaigns should be live within the first 2 months. Reporting will be until the end of the Agreement. According to the partnerships and results achieved, the contract could be extended for additional 2 years.

Agreement size: Up to $150,000 for selected partner. Please make sure you identify fixed costs for development, costs you will not be incurring thanks to the fact that you are leveraging previous similar work done, and variable costs per user. According to the partnerships and results achieved, the selected partner may be awarded with additional funding for the scale up.

- Partner selection process

A –ELIGIBILITY CRITERIA

- Any type of organization (commercial for-profit firms, educational institutions, and non-profit organizations) qualified to perform the required services may compete for this contract is eligible to compete

- At least 12 months in operations

- Demonstrable experience developing and running crowdfunding platforms particularly in a development context, for development organisations, and in developing countries

- Have confirmed human resources to cover all planned/required activities

- Please make sure you submit ALL docs required:

  - Provide written confirmation (Annex 1) that the organization has reviewed the UNCDF Grant Agreement template (available upon request at youthstart@uncdf.org ), and that your organization is prepared to sign it without revision to standard language

  - Submit a complete application (Annex 2) in Word format

  - Detailed budget with cost of platform development (technology), training and related activities with beneficiaries and support services

  - Supporting documents:

    - Financial statements of the past year duly certified by a public accountant (only for lead applicant)

    - Article of incorporation

    - CV of staff involved in the Project

    - Staff time allocation spreadsheet per activity

    - Evidence of similar platforms produced under similar assignments (this can be reports to donors or links in a website, for example).

B. EVALUATION PROCESS

UNCDF will conduct a desk review to screen the candidates and will evaluate the proposals as follows:

| Bidder's qualification, capacity and experience | 300 |
| --- | --- |
| Type of organization | 50 |
| General Business model which is likely to affect implementation | 50 |
| Profitability and sustainability of the organization(s) | 50 |
| Previous experience relevant for this RfA | 150 |
| Approach & Implementation | 400 |
| Approach to the Results Required | 150 |
| Activities and Timelines are well defined and in line with project expectations | 50 |
| Plan to scale up the strategy proposed (exit strategy and sustainability) | 100 |
| Key Project Indicators: KPIs in line with project expectations and good value for money | 50 |
| Key Project Risks are well identified | 50 |
| Team (Key personnel) | 200 |
| Composition and structure of the key team proposed | 100 |
| Time Allocation of personnel | 50 |
| Key skills and competencies of team members | 50 |
| Budget | 100 |
| The budget proposed is in line with project objectives (value for money) | 100 |
| GRAND TOTAL | 1000 |

Clarification of Applications

To assist in the examination, evaluation and comparison of applications, UNCDF may, at its discretion, ask any applicant for a clarification of its proposal.

UNCDF’s request for clarification and the response shall be in writing. Notwithstanding the written communication, no change in the prices or substance of the proposal shall be sought, offered, or permitted, except to provide clarification, and confirm the correction of any arithmetic errors discovered by UNCDF in the evaluation of the Proposals.

Any unsolicited clarification submitted by an applicant in respect to its proposal, which is not a response to a request by UNCDF, shall not be considered during the review and evaluation of the proposals.

A tentative calendar of the selection process is as follow

- April 17: Launch of the RFA

- April 24 : deadline to submit questions to youthstart@uncdf.org

- April 30 1pm GMT+0: deadline for submission of RFA application. Proposals must be sent by email to youthstart@uncdf.org , mentioning the subject of the message “Crowdfunding Platform for UNCDF Ghana Programme”

- May 6: Review of the RFA, ensuring that all questions and requests for documents are duly completed; shortlist of candidates.

- May 13: final selection of the partners and signature of a Performance Based Agreement (PBA) with UNCDF

Only complete applications will be considered. Please make sure that ALL annexes are submitted

APPENDIX 1: Template for the application

[Insert: location]

[Insert: Date]

To: Maria Perdomo, Youth Finance Global Specialist

Dear Madame:

[

We the undersigned [insert: name] as candidates for the Development of a Crowd-Funding Platform in Ghana project in accordance with your Call for Expressions of Interest dated [insert: date]. We present our application, which includes the technical proposal.

We hereby declare that:

a) All information and statements made in this application are true and we accept that any misrepresentation contained therein may result in our disqualification; and

b) We have no outstanding bankruptcy or ongoing litigation or any legal action that could adversely affect our business

c) If we are selected, the organization is fully committed to the execution of the agreement and commitment in the process

We confirm that we have read, understood and accept the duties and responsibilities that are requested in this request for Application (RFA), as well as the standard language of UNCDFs performance-based agreements (PBAs), including the public good requirements and knowledge products to be shared. Therefore, if our request is accepted, we will be ready to sign and accept the legal language, without modification, of the UNCDF Grant Agreement (PBA).

We fully understand and acknowledge that UNCDF is not obliged to accept this request, that we will bear all costs associated with its preparation and submission, and that UNCDF will not be responsible for these costs, regardless of the conduct or results evaluation.

We remain at your disposal,

Regards,

Authorized signature [In full and initials]:

Name and title of the signatory:

Company Name:

Contact Details:

[Please mark this letter with your corporate seal, if available]

ANNEX  2 : Application Form

| SECTION 1: GENERAL INFORMATION ON THE CANDIDATE |  |
| --- | --- |
| Exact Name of the Organization (as it will appear on the agreement): |  |
| Type of Organization (for example, for-profit commercial enterprise, non-profit organization, etc.): |  |
| Country of registration: |  |
| Year of registration: |  |
| Actual or intended Country/ies of Registration/Operation and number of staff in each country |  |
| Please name your external auditors |  |
| Brief description of litigation history (disputes, arbitration, claims, etc.), indicating current status and outcomes, if already resolved |  |
| In case of Joint Venture (JV), legal name of each party, including lead applicant and specific roles of each partner |  |
| Attached are copies of original documents of: ☐ Financial statements for the past year duly certified by a public accountant ☐Letter in appendix 1. ☐Complete CVs of all the team members involved in the assignment ☐ Staff time allocation spreadsheet per activity ☐Evidence of similar platforms produced under similar assignments (this can be reports to donors or links in a website, for example). |  |
| Licensing model of the Applicant (if applicable): Please specify the cost structure of the licensing models (e.g. sustainability of the platform) |  |
| Please note if your organization is receiving technical assistance services from other donors, which are the areas of intervention, if there are opportunity for synergies or risk of overlapping |  |

| SECTION 2: DESCRIPTION OF THE ORGANISATION AND STRATEGY |  |
| --- | --- |
| Type of organization | [Outline if it is a private or public entity, Fintech, NGO and/ or donor agency] |
| Business Model & Vision | Please provide a brief outline of the business model Explain the value proposition [When describing the value proposition, explore the various dimensions. ] - Product and services offered - Customer segment served/intended to be served - Marketing strategies - Complementary non-financial services for the platform - Financial model and key sources of revenues and expenses (brief description) - Partnership established with other entities] How the your institution wants to expand and how this project can support your expansion and quality of services provided |
| Key figures in the past three years of operations [in case it is a start-up, provide current figures and projections]. Explain also if your institution can provide sex and age disaggregated data on platform users. | [In this section, you are expected to complete the table with the relevant ops and financial indicators and then making a brief analysis, by explaining any variation of those indicators. If platform users reduce or increase dramatically, if number of active merchants is much lower than registered merchants etc.] #; Main Performance indicators*; 2019; 2018; 2017. 1; # of platform users. 1.a; % of female users. 1.b; % of users between 18 and 25 years old. 2; # of businesses that successfully raise funds. 2.a; % of women-led businesses. 2.b; % of youth-led businesses. 3; Volume of funds mobilised. 2.a; Funds mobilised from diaspora. 2.b.; Funds mobilised from domestic sources. 4; # of platform users receiving support services (i.e. training). Revenues. ROA. ROE. Profit margin. *If in multiple countries, provide one table with the aggregated data and one table per country |
| Previous experience relevant for this RfA | [Please describe your institution’s experience with crowdfunding platforms in particular in sub-Saharan Africa and in response to emergency crisis. If present in more than one country, please be specific]. |

SECTION 3: APPROACH AND IMPLEMENTATION (max 3 pages) (if the work or part of it is delegated, please specify the rational, roles and responsibilities)

3.1. Approach to the Results Required: Please provide a detailed description of the methodology for how the organisation/firm will achieve project outputs, keeping in mind the appropriateness to local conditions and project environment. Please make sure you take into consideration the specificities listed under “objective of the RfA”, section 2.

3.2. Activities and Timelines: The Applicant shall submit a Gantt Chart or Project Schedule indicating the detailed sequence of activities that will be undertaken and their corresponding timing, specifying timelines, and time devoted to each activity. Please make sure you detailed the activities requested under section 3. Phase/Activity; Main Deliverables; Responsible Party; Planned date. Phase 1- Activity 1. Phase 1- Activity 2.

3.3 Plan to scale up the strategy proposed: please provide a tentative plan (“exit strategy”) to ensure sustainability and extend the platform once the grant agreement is over.

3.4 Key Project Indicators: Please make sure you explain the hypothesis behind the projections. Add KPIs that you think are relevant for your proposal. Please define what you mean by each indicator to avoid misunderstanding. #; Main Performance indicators; 2020; 2021; 2022. 0; Number of new or improved business model piloted or scale up within the project. 1; # of platform users (registered customer). 1.a; % of female users. 1.b; % of users between 18 and 35 years old. 2; # of businesses that successfully raise funds. 2.a; % of women-led businesses. 2.b; % of youth-led businesses. 3; Volume of funds mobilised. 2.a; Funds mobilised from diaspora. 2.b.; Funds mobilised from domestic sources. 4; # of platform users receiving support services (i.e. training). % of female users. % of users between 18 and 35 years old. Please add KPIs that you think are relevant for your proposal.

3.5 Key Project Risks Description of risk; Likelihood; Impact; Mitigation measure. High probability; Negligible. Marginal. Critical. High probability; Catastrophic. Medium probability; Critical. Low Probability.

SECTION 4: TEAM (max 3 pages)

4.1 Composition and structure of the key team proposed: Briefly describe the qualifications of at least 5 members of your institution who will be involved in this project (for example, financial services promoter for youth, director of market research or new products, etc.)

4.2 Staff Time Allocation: Briefly provide the level of effort and time allocation of the staff members mobilized. Project team. Name; Function; Responsibility in the project; Full time/ Part time; Contact details (email/tel).

4.3 Qualifications of Key Personnel. Provide CVs for key personnel (team leader, management and general staff) that will be provided to support the implementation of this project. CVs must demonstrate qualifications in areas relevant to the outputs to be produced. CVs must not exceed 5 pages and should follow the format below: Name:. Position for this Contract:. Nationality:. Contact information:. Countries of Work Experience:. Language Skills (make sure to mention if the team member speaks local languages):. Educational and other Qualifications:. Summary of Experience: Highlight experience in the region and on similar projects.. Relevant Experience (From most recent):. Period: From – To; Name of activity/ Project/ funding organisation, if applicable:; Job Title and Activities undertaken/Description of actual role performed:. e.g. June 2019-January 2020. Etc.. Etc.. Referencesno.1 (minimum of 3):; Name Designation Organization Contact Information – Address; Phone; Email; etc.. Reference no.2; Name Designation Organization Contact Information – Address; Phone; Email; etc.. Reference no.3; Name Designation Organization Contact Information – Address; Phone; Email; etc.. Declaration: I confirm my intention to serve in the stated position and present availability to serve for the term of the proposed grant agreement. I also understand that any wilful misstatement described above may lead to my disqualification, before or during my engagement. _________________________________________________ __________________________ Signature of the Nominated Team Leader/Member Date Signed.

SECTION 5: BUDGET & DISBURSEMENT CONDITIONS

[The partner institution is asked to provide a detailed budget with a breakdown by cost and/or activity/phase and components. Budgets should be also provided in excel to verify the correctness of all formulas.

Please make sure you detail the cost for developing the platform, for training and related activities with beneficiaries and support services.

| Cost component/ Phase | Unit/consultant | Unit price (USD) | Quantity/day | Total (USD) |
| --- | --- | --- | --- | --- |
| Total |  |  |  |  |

The budget needs to include the disbursement tranches. The disbursement tranches should be linked to the attainment of the KPIs (number of beneficiaries reached) the main deliverables mentioned in section 3 and the submission of the quarterly and quantitative report to UNCDF].

| # of tranches | % of total loan/grant | Amount US$ | Estimated date of Execution | Disbursement conditions for payment execution |
| --- | --- | --- | --- | --- |
| Total Budget |  |  |  |  |

SECTION 6: FINANCIAL CONTRIBUTION OF THE PARTNER INSTITUTION

The costs that the partner institution will take in charge in addition to mobilizing dedicated human resources:

| Cost category | Detail of partner’s contribution |
| --- | --- |
| International travel |  |
| Domestic transportation |  |
| Workshop |  |
| Training material |  |
| In-kind |  |
| Other |  |

If the quick win action meets the objectives, the selected partner can be awarded with additional funding to scale up the solution.