UNITED NATIONS CAPITAL DEVELOPMENT FUND (UNCDF)

Innovation Hub  – Multiple Cohorts and Accelerator Engagement

REQUEST FOR APPLICATIONS

Deadline for submission:  17th  of September 2018

- INTRODUCTION TO THIS REQUEST FOR APPLICATIONS

UNCDF is looking for a firm or a consortium of other related stakeholders like universities, advisory non-profit organizations to support with expert guidance the set-up of an innovation hub in multiple countries in Asia and Africa, starting with Nepal. The innovation hub will undertake different activities over the course of next few years to support the development of digital solutions that address the needs of different segments and sectors.

The result of this process will be creation of new SMEs/Start-ups that will bring in innovative services to the Nepali and other UNCDF markets and they will give impetus to the digital economy, thus creating jobs and driving growth. UNCDF will support the incubation/acceleration process of new ideas or existing solutions. This process referred to as “cohort” will bring-in different types of support as listed below.

- Mentoring: opportunity to work alongside industry leaders and experienced investors to catalyze growth.

- Access to support infrastructure, collaboration tools and digital platforms.

- Knowledge Sharing: sharing know-how within global and local tech community members and start-up founders.

- Strategic and global access to subscribers/clients, as well as insights to shape future technologies from the enabler partners.

- Investment capital to fund early-stage companies working across use-cases where digital is a key enabler

The Innovation hub at country level plans to conduct at least four cohorts to support the creation of new SMEs/ start-ups. Each country has its own focus in terms of nos, the above mentioned number is for Nepal, but the few cohorts could also be asked to be delivered in other markets of Asia or Africa. Each cohort will focus on a specific topic and applicants will have to apply based on list of a pre-defined criteria. Agriculture, health, finance, education, remittance represent a list of the sectors under which these new SMEs would be supported to create digital solutions that address variety of pain points.

UNCDF will support the selected applicant, by bringing in the expertise of its innovation team in Asia and other markets in the region to apply the tools within each cohort and work with a network of mentors at national, regional and global level.

The overall duration of the engagement is expected to take up to 24 months.

Applications & RFA Calendar:

- Publication date: 24 August 2018

- Deadline for questions in writing 30 August 2018

- Publication of Questions and Answers Document: 3 September 2018

- Final deadline for applications 17th  September 2018 6pm GMT

You may send questions to mm4p@uncdf.org A FAQ document will be generated based on enquiries received on or before 30 August. The FAQs will be posted on the UNCDF website no later Monday the 3rd of September.

Applications should be returned to the UNCDF by email at mm4p@uncdf.org no later than midnight on 17th September Greenwich Mean Time (GMT). Applications must follow the submission format in Annex I.

  - Purpose of the RFA

UNCDF with its focus on digital finance and innovations, is promoting digital innovations anchored through an in-country hub that serves as incubator and accelerator of meaningful digital solutions for different sectors and segments especially low-income customers.

As part of the hub, UNCDF is preparing to announce the first cohort in 2018 that would focus on inviting pre-seed stage or legally established start-ups with minimum viable product (MVP) that address problem in the space of agriculture, health, citizen interaction where digital is a key anchor and finance (at-least payment) a clear enabler for driving growth. Funding for the first cohort would come from UNNATI programme of UNCDF. The series of other cohorts would be launched in 2019 and 2020.

The purpose of this request for applications (RFA) is to engage the services of an organization or consortium of organization that could  engage in the space of digital innovation whose results are linked to UNCDF’s capital mandate to provide capital  grants, loans and guarantees) and technical support. This RFA will result in selecting one potential organization/ consortium with whom UNCDF will support launch provide expert guidance and manage the four cohorts.

UNCDF will provide a grant and sign a performance-based agreement with the selected organization or the leading organization of the consortium to attain the following results:

- Successful completion of Cohort 1 with the results documented and linkages made with the enablers;

- Successful Completion of Cohort 2-4 with the process documented and linkages made with enablers for scale.

- Refine the tools and curriculum to be delivered under the individual cohorts, accomplished alongside UNCDF team

- Support in refining the problem statements and the eligibility criteria for the four cohorts.

- Support with structuring of the mentorship engagement with both global and local pool. Along with facilitate bringing in the expertise required for specific intervention.

- Support with the process under Cohort 1 from application to bootcamp to mentorship to connection.

- Support with the process under Cohort 2-4 from application to design sprint to accelerators to scale-up

- Support on structuring the tools and the role of enablers on-boarded during the cohorts, going alongside the sandbox environment that would be needed to test solutions.

- Supporting UNCDF in developing the required connection on capital side that would allow new blended finance engagement to be deployed in country for supporting investments in the SMEs

- Working with UNCDF communication team in enhancing visibility, engaging relevant partner and strengthening the hub network;

Proposals should have a strong public good component and the people supporting the initiative would be critical and should have depth of knowledge in space of digital finance and working with use-cases.

All applicants should give full consideration to the Principals of Digital Development.

  - Timing

Applications should be returned to the UNCDF by email no later than midnight on 17th September 2018 Greenwich Mean Time (GMT).  It is anticipated that shortlisting will be completed within 2 weeks of application submission.  The time needed for submission of revised proposals, if needed, will depend on the complexity and thoroughness of the initial proposals but should take no more than three weeks. UNCDF would like to conclude all agreements no later than fourth week of September.

Activities are expected to start at the end of September 2018. The expected date of full completion of first cohort up-to boot-camp leading to solutions enablement is no later than 31 December 2018., while for the cohorts 2-4 will be September 2019

The overall duration of this phase of engagement with in-country hub is expected to be for a period of 24 months and further extended for 12 months based on performance and funding availability.

  - Contact

Applications and any consultation about this RFA should be submitted via email at mm4p@uncdf.org

  - Responses

All queries and submitted applications will be acknowledged. A FAQ document will be generated based on enquiries received on or before 30th of August September.  The FAQs will be posted on the UNCDF website on the 3rd of September.

- ORGANIZATION CONTEXT AND BACKGROUND INFORMATION

  - Organization Context

The UN Capital Development Fund (UNCDF) makes public and private finance work for the poor in the world’s 47 least developed countries. With its capital mandate and instruments, UNCDF offers “last mile” finance models that unlock public and private resources, especially at the domestic level, to reduce poverty and support local economic development. UNCDF’s financing models work through two channels: financial inclusion that expands the opportunities for individuals, households, and small businesses to participate in the local economy, providing them with the tools they need to climb out of poverty and manage their financial lives; and by showing how localized investments—through fiscal decentralization, innovative municipal finance, and structured project  finance—can drive public and private funding that underpins local economic expansion and sustainable development. By strengthening how finance works for poor people at the household, small enterprise, and local infrastructure levels, UNCDF contributes to SDG 1 on eradicating poverty and SDG 17 on the means of implementation. By identifying those market segments where innovative financing models can have transformational impact in helping to reach the last mile and address exclusion and inequalities of access, UNCDF contributes to a number of different SDGs.

  - Background Information about UNCDF and Digital Finance

UNCDF manages a number of digital financial (DF) initiatives to address the challenges of implementing branchless banking and mobile money in least developed countries (LDCs) in Africa and Asia, as well as in emerging markets and middle-income countries. UNCDF’s long-term mission is to help low-income and rural households in LDCs to enhance their financial security through appropriate, affordable and secure means to receive, manage and save money through “digital financial services” (DFS). UNCDF goal is to help build inclusive digital financial sectors to assure that DFS are provided responsibly, at reasonable cost, by sustainable institutions in a well-regulated environment.

UNCDF pursues a market development approach to digital finance. UNCDF characterizes the evolution of the market as occurring in four phases: Inception, Start-Up, Expansion and Consolidation. To summarize, Inception is when a market has only a few actors with limited outreach that are working without clear policies or supporting DFS infrastructure. In contrast, Consolidation is when a market has a range of competitive actors and services that are clearly regulated and interconnected. Expansion is the critical phase when several players are gaining scale, reaching sustainability and increasing investment.

UNCDF has d been using a range of interventions to move the market through the different phases, by providing policy advice, technical support, training and financing.

UNCDF has recently begun working on “digital finance plus,” looking at how it can focus on specific use cases for DFS around essential services, such as energy, education, social protection, and informal savings.

- SCOPE OF WORK

The selected applicant is expected to support the operations and management of the activities under the innovation hub in Nepal and other countries which may include Malaysia and beyond, through an incubation/acceleration structure

The broader contours of this engagement are as listed below and would be reviewed/updated based on discussion with UNCDF.

| Phase/Activity | Deliverables | People Responsible |  | Potential Period |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Cohort 1 |  |  |  |  |  |  |
| Setting the problem statement and the eligibility criteria for the cohorts | - Document/PPT outlining the challenge and the criteria for selection |  | Selected Firm and UNCDF |  | Sep – Oct 2018 |  |
| Announcement of the cohort using different form of media channels and road-shows | - PPT with listed channels deployed and proof of dissemination |  | Selected Firm |  | Oct –2018 |  |
| Structuring the mentorship and technical engagement necessary to support the process and engage with the start-ups | - Listing of mentors with their skills and signed LoI for engagement with them during the course of the programme |  | Selected Firm closely engaging with global UNCDF team working on same |  | Sept.– Oct. 2018 |  |
| Identifying the enablers for the cohort and orientation on the engagement | - List of enablers documented |  | Selected Firm |  | Sept. – Nov 2018 |  |
| Defining and developing the curriculum and tools to be deployed for cohort one process including tools like human centered design | - Tools and training and mentorship and acceleration/incubation curriculum and modules developed |  | Selected firm and UNCDF |  | Sep – Nov 2018 |  |
| Selection of the applicants | - List of applicants with the identified mentors to engage and required technical assistance |  | Selected Firm |  | Nov 2018 |  |
| Bootcamp Implementation and Management | - BootCamp event - Bootcamp report and KM coverage - Brief document outlining the outcomes, along with KPIs and road-map |  | Selected Firm |  | Dec 2018 |  |
| Contribute to reporting, outreach and communication efforts where necessary, including preparation of project briefs, presentations, promoting project events to key stakeholders, etc.. Help to increase public's knowledge of the project activities, with the focus on strengthening UNCDF online presence including the web-site and social networks like Facebook and Twitter | - project brief |  | Selected firm and UNCDF team |  | Dec. 2018 |  |
| Ensure the collection and analysis of relevant M&E data. Prepare portfolio results for program reports, including those required by the UNCDF | - key KPIs captured and monitored - Progress reports |  | Selected Firm and UNCDF |  | Dec.2018 |  |
| Support in gathering and producing learnings from different challenges, acceleration and scale process and then further implementation under them. | - Documented learning questions and preparation - one blog article |  | Selected Firm and UNCDF |  | Dec.2018 |  |
| Cohort 2 – 4 Upon satisfactory performance and delivery of cohort 1, the selected organization will be contracted to develop a new set of at least three cohorts (indicatively one per semester). Please note that the list of activities is not exhaustive, but indicative |  |  |  |  |  |  |
| Setting the problem statement and the eligibility criteria for the cohorts | - Document/PPT outlining the challenge and the criteria for selection | Selected Firm and UNCDF |  | Apr 2019 – Jan 2020 |  |  |
| Announcement of the cohort using different form of media channels and road-shows | - PPT with listed channels deployed and proof of dissemination | Selected Firm |  | Apr 2019 – Jan 2020 |  |  |
| Selection of the applicants | - List of applicants with the identified mentors to engage and required technical assistance | Selected Firm |  | Jun 2019 – Mar 2020 |  |  |
| Refining the curriculum and tools to be deployed for cohort one process including tools like human centered design and other technical tools that needs to be deployed based on nature of solutions expected | - Collated tools and curriculum organized for the cohort within the drop-box | Selected firm and UNCDF |  | Cohort Two: Apr – Jun 2019 Cohort Three: Sep – Nov 2019 Cohort Four: Feb – Mar 2020 |  |  |
| Identifying the enablers for the cohort and orientation on the engagement | - List of enablers documented - MoU signed with key enablers | Selected Firm |  | Oct 2018 – April 2020 |  |  |
| Structuring the mentorship and technical engagement necessary to support the process and engage with the start-ups | - Mentor database outlining Country, competencies, skills and signed LoI for engagement with different mentors | Selected Firm closely engaging with global UNCDF team working on same |  | Oct 2018 – April 2020 |  |  |
| Design Sprint/Product Development Implementation and Management | - Brief document outlining the outcomes and road-map | Selected Firm |  | Jul 2019 – Apr 2020 |  |  |
| Pre-Accelerator/Accelerator Phase Implementation and Management | - Brief document outlining the outcomes for the participants | Selected Firm |  | Aug 2019 – May 2020 |  |  |
| Pilot Testing and Scale-up engagement with the participants | - Report on individual participant moving into pilot and scale-up | Selected Firm |  | Sep 2019 – Sep 2020 |  |  |
| Supporting in identification and then further structuring of the engagement to link-up with Investment Community | - Supporting due-diligence and linkages for those participants ready to receive capital | Selected Firm closely engaging with global UNCDF team working on same |  | Oct 2018 – Sep 2020 |  |  |
| Support with participant coordination, including ensuring efficient communication with those participating under UNCDF innovation hub and its related activities | - Documented communication plan for the engagement | Selected firm and UNCDF team |  | Oct 2018 – Sep 2020 |  |  |
| Contribute to reporting, outreach and communication efforts where necessary, including preparation of project briefs, presentations, promoting project events to key stakeholders, etc.. Help to increase public's knowledge of the project activities, with the focus on strengthening UNCDF online presence including the web-site and social networks like Facebook and Twitter | - Proof of dissemination | Selected firm and UNCDF team |  | Oct 2018 – Sep 2020 |  |  |
| Work with UNCDF on activating the community of practice by way of both physical and virtual engagements | - Brief Documented Outcomes of the interventions | Selected firm and UNCDF |  | Oct 2018 – Sep 2020 |  |  |
| Ensure the collection and analysis of relevant M&E data. Prepare portfolio results for program reports, including those required by the UNCDF | - key KPIs captured and monitored | Selected Firm and UNCDF |  | Jan 2019 – Sep 2020 |  |  |
| Support in gathering and producing learnings from different challenges, acceleration and scale process and then further implementation under them. | - Documented learning questions and preparation of at-least one blog per cohort | Selected Firm and UNCDF |  | Dec. 2018 – Sep 2020 |  |  |
| - Foreseen budget |  |  |  |  |  |

The applicants are invited to submit a budget clearly outlining the costs for the implementation of cohort 1 and separately for cohorts 2-4.

The first grant will be focusing on the implementation of cohort 1. Upon satisfactory performance of cohort 2 and 4, a second grant will be extended to cover the second phase.

- PARAMETERS OF THE AGREEMENT

Outputs and deliverables

[The written outputs and deliverables of the work are considered a public good unless otherwise agreed. Thus, all the outputs and deliverables will be placed in the public domain with the intent that they can and should be freely and widely used by other parties.]

Agreement

[The technical partner is expected to sign a Performance Based Financing (Grant) Agreement with UNCDF (see Annex 2 for a sample of our legal language in this regard. Applicants not familiar with UNCDF agreements are encouraged to request a sample from mm4p@uncdf.org prior to submission of application). ]

Language

[The deliverables, as well as any and all related correspondence exchanged by the organization and UNCDF, shall be written in English.]

- Eligibility criteria and APPLICATION REQUIREMENTS

  - Eligibility requirements

- Applicant(s) should be duly registered in its country of incorporation;

- Not to be in a state of repair or to have been the subject of bankruptcy, liquidation, judicial settlement, safeguarding, cessation of activity or any other similar situation resulting from a similar procedure;

- Not to be included in the United Nations financial sanctions lists, particularly in the fight against the financing of terrorism and against attacks on international peace and security;

- To have fulfilled obligations relating to the payment of social security contributions or obligations relating to the payment of taxes according to the legal provisions in its country of incorporation;

  - Minimum qualification criteria

- Experience of person(s) managing the selected firm would be crucial. The persons engaged should have a background in space of digital finance and innovation at global level.

- Successfully conducted similar assignments at a country or regional level either in individual capacity or as a firm with proven excellent results, including financial services and other development issues

- Ability to work in the language of the country / ies proposed (i.e. English)

- Submit a complete application

  - Structure of the Application

- The application includes a suggested template for submissions in Annex 1: Submission Format.  Section 1 must be followed as in the Annex.  Applications may choose a format for sections 2, 3 and 4 provided all the necessary information is included.

- Additional documents or links to documents may be included at the applicant’s discretion.

  - Submission of the Application

- Applications and any consultation about this RFA should be submitted via email at mm4p@uncdf.org

- The subject line of the email should be:  RFA:  Innovation Hub – Managing Multiple Cohorts

- The deadline to submit the applications is 17th September 2018 at midnight Greenwich Mean Time

- EVALUATION CRITERIA

The evaluation will follow the combined scoring method:

Rating the Technical Proposal (TP):

TP Rating = (Total Score Obtained by the Offer / Max. Obtainable Score for TP) x 100

Rating the Financial Proposal (FP):

FP Rating = (Lowest Priced Offer / Price of the Offer Being Reviewed) x 100

Total Combined Score:

(TP Rating) x (Weight of TP, e.g. 70%)

+ (FP Rating) x (Weight of FP, e.g., 30%)

Total Combined and Final Rating of the Proposal

Technical proposal (including CVs of team): 700 Points

Expertise of the Firm; Points Obtainable. Expertise of the firm in digital finance and innovation space. Experience working with start-ups/entrepreneurs with focus on financial inclusion and low-income segments with be of added advantage; 125. At least ten year demonstrated track record of the management team in implementation of digital finance and innovation related engagements; 200. Quality assurance procedures and mechanism, guarantee provided by the individual in lead or firm; 75. Total Part 1; 400. Understanding of the mandate and proposed approach; Points Obtainable. The proposal addresses the requirements laid out in the milestone section appropriately; 100. The design of the proposed approach is structured, and appropriate to UNCDF requirements and to achieve the gaols; 100. The proposal presents efficient and cost-effective measures ways to manage the implementation; 100. Total Part 2; 300.

Financial Proposal (300 points)

Only the financial offers of the applicant scoring at least 70% of the technical proposal will be

To be computed as a ratio of the Proposal’s offer to the lowest price among the proposals received by UNCDF.

Total 1,000 points.

ANNEX 1: SUBMISSION FORMAT

[insert: Location]

[insert: Date

To:	Carlos Escrivá Gil, Operations Analyst, and MM4P

Dear Sir

We, the undersigned, hereby apply for Innovation Hub  in accordance with your Request for Application dated [insert: Date] and our Application.  We are hereby submitting our Application, which includes the Technical Proposal including proposed budget allocation.

We hereby declare that:

- All the information and statements made in this Application are true and we accept that any misrepresentation contained in it may lead to our disqualification; and

- We have no outstanding bankruptcy or pending litigation or any legal action that could impair our operation as a going concern

We confirm that we have read, understood and hereby accept the duties and responsibilities required of us in this RFA, and the standard language of UNCDF’s Performance Based Agreements (PBA), including the requirements regarding the public good nature of the outputs to be produced (see Annex 2 for a sample of our legal language in this regard.

We fully understand and recognize that UNCDF is not bound to accept this application that we shall bear all costs associated with its preparation and submission, and that UNCDF will in no case be responsible or liable for those costs, regardless of the conduct or outcome of the evaluation.

We remain,

Yours sincerely,

Authorized Signature [In full and initials]:

Name and Title of Signatory:

Name of Firm:

Contact Details:

[Please mark this letter with your corporate seal, if available]

Page ________of ________ pages

SECTION 1: GENERAL APPLICANT’S INFORMATION

- Applicant’s Legal Name:

- Type of Organization (e.g. commercial for profit firm, educational, non-profit, etc.):

- In case of Joint Venture (JV), legal name of each party:

- Actual or intended Country/ies of Registration/Operation:

- Year of Registration:

- Countries of Operation / No. of staff in each Country / Years of Operation in each Country

- Legal Address/es in Country/ies of Registration/Operation

- Description and value of top three grants or contracts relevant to the scope of this RFA for the past five years. Provide the following information for each of them.

- Name of the project (website if applicable):

- Date, location:

- Client/Funder (if applicable):

- Grant/Contract value in USD:

- Types of results produced/activities undertaken:

- References, contact details (name, position, email, phone number):

- Applicant’s Authorized Representative Information

- Name:

- Address:

- Telephone/Fax numbers:

- Email Address:

- Are you in the UN Ineligibility List?  ☐ YES or ☐ NO

- Attached are copies of original documents of:

☐ Financial statements for the past 2 years (in English or French)

☐Letter from the applicant organization’s executive director, CEO, or board, expressing its commitment to the execution and participation in this process

☐Complete resumes of all the team members involved in the assignment

☐ Staff time allocation spreadsheet per result

☐Electronic copies and hyperlinks where available of studies, knowledge products produced under similar assignments and list of dissemination channels

SECTION 2: SPECIFIC EXPERIENCE FOR THE ASSIGNMENT

- Please describe your organization’s experience in producing similar projects. For each one, make sure you describe the following (maximum 1 page per project up to 5 projects):

- Name of the project (website if applicable);

- Client/Funder (if applicable);

- Grant/Contract value;

- Description of the approach/methodology;

- Types of outputs/deliverables produced and activities undertaken;

- Tools used or developed (dashboards, maps, etc.);

- Results of project for client, if known;

- Time it took you to complete the assignment, dates, location;

- Number of people and names of the staff that participated in the assignment;

- Knowledge product production and dissemination strategy of the assignment;

- References, contact details (name, position, phone number, email);

- The applicant should describe your organization’s expertise in managing incubator or accelerator programme and the key insights, lessons learned or other takeaways from this work not mentioned in no. 12 above. (maximum 6 pages)

  - The applicant should describe their specific experience related to managing the challenge windows and methodology deployed around accelerator programme, providing more in depth explanation on specific tools with an emphasis on their relevance, accessibility and use by participants

  - Experience in the relevant country/ies

- The applicant shall clearly state the tools and content that they intend to bring in terms of methodology to support the process from design to prototyping   (maximum 1 page)

- The applicant should describe the team, knowledge product production, packaging and dissemination process of your organization (maximum 2 page)

- The applicant should note their organization policies around legal and ethical use of methodology or content or data and provide copies or links, if available.

SECTION 3: APPROACH AND IMPLEMENTATION PLAN (10 pages)

- Approach to Scope of Work and Proposed Deliverables

The applicants should propose a scope of work.  As noted the applicant may suggest an alternative scope of work and / or deliverables that achieves the same objectives.  However, the applicant should address each component of the SOW in Section 3 of the RFA, even if they are proposing to do very little in that component.

- Identify the county/ies of work

- Note

  - the availability of data, present and future

  - expertise in or relationships specific countries or with specific stakeholders or development issues

- Address all issues in section 3.1 of the SOW, Expected Activities and Outputs, including:

  - working with stakeholder to identify and select use cases/challenge

  - validating analysis/design process and further accelerator

  - assisting in pilots, projects to act on findings

  - assessing the value, success of the prototypes.

Highlight the type of support or guidance you would need from UNCDF.

- Describe the proposed tool 
The applicant should describe the tool and may provide links to prototypes or similar tools for review. Indicate if it will be newly developed or adapted from existing tools; on-going support provided or needed for maintenance or adaptation; user-friendliness; plan to make some or all accessible beyond the applicant and UNCDF.

- Approach to the Implementation and working with the MM4P Team

The applicant should provide a detailed description of how the applicant will plan, implement and deliver the overall project. Indicate the type of team, resources that the applicant will provide, how it will organize itself for the work.  Pay specific attention to the appropriateness to local conditions and project environment.  Highlight the support it would need from UNCDF.

- Approach to Communications

The applicant should provide detail on what type of knowledge products from deliverables and how it prefers to communicate the progress and results on the overall project as noted in section 3.3 of the RFA. Also note what support would be needed from UNCDF.

- Approach to legal compliance, data privacy and security, and ethical use of data

The applicant should clear state how it will protect customer data privacy and security and the extent to which the proposed project will comply with of the Principles of Digital Development.  For principles that cannot be upheld in the project, the applicant should clearly state the reasons.  The applicant should note how it intends to ensure that its work is in compliance with local laws and regulations.

- Implementation Timelines

The applicant shall submit a Gantt Chart or Project Schedule indicating the detailed sequence of phases, activities that will be undertaken and their corresponding timing, specifying timelines, responsibility, and time devoted to each result.  Start date should be no sooner than 15 March 2016.

- Risks / Mitigation Measures

Please describe the potential risks for the implementation of this project that may impact achievement and timely completion of expected results as well as their quality.  Describe measures that will be put in place to mitigate these risks. The applicant should address issues around data privacy and security.

- Technical Quality Assurance Review Mechanisms

The methodology shall also include details of the applicant’s internal technical and quality assurance review mechanisms.

SECTION 4: PERSONNEL

- Management Structure

Describe the overall management approach toward planning and implementing this result.  Include an organization chart for the management of the project describing the relationship, roles and responsibilities of key positions and designations.

- Sub-grantees, contractors or other critical relationships

Explain whether any work would be delegated, to whom, how much percentage of the work, the rationale for such, and the roles of the proposed sub-grantees or contractors.  Special attention should be given to providing a clear picture of the role of each entity and how everyone will function as a team. If there are any other critical relationships or partnerships, please highlight them here.  For other organizations that play a substantial role (e.g.  > 25% of time or cost), please provide items 1 thru 8 in Section 1of this Annex.

- Staff Time Allocation

Provide a spreadsheet to show the activities of each staff member and the time allocated for his/her involvement.  Please describe any travel/missions/field visits planned for this assignment indicating team member participation and duration.

(Note: Substitution of key personnel will once the grant has been awarded will be subject to the written approval of UNCDF.  No increase in grant will be considered as a result of any substitution.)

- Qualifications of Key Personnel

Provide the CVs for key personnel (Team Leader, Managerial, Technical experts) that will be provided to support the implementation of this project. CVs should demonstrate qualifications in areas relevant to the results to be produced.

In addition to the CVs, please submit a summary for each person in the following format:

| Name: |  |  |  |
| --- | --- | --- | --- |
| Position for this Contract: |  |  |  |
| Nationality: |  |  |  |
| Contact information: |  |  |  |
| Countries of Work Experience: |  |  |  |
| Language Skills: |  |  |  |
| Educational and other Qualifications: |  |  |  |
| Summary of Experience: Highlight experience in the region and on similar projects. |  |  |  |
| Relevant Experience (From most recent): |  |  |  |
| Period: From – To | Name of Organization/Project/Activity, if applicable: |  | Job Title and Activities undertaken/Description of actual role performed: |
| e.g. June 2015-January 2016 |  |  |  |
| Etc. |  |  |  |
| Etc. |  |  |  |
| References no.1 (minimum of 3): | Name Designation Organization Contact Information – Address; Phone; Email; etc. |  |  |
| Reference no.2 | Name Designation Organization Contact Information – Address; Phone; Email; etc. |  |  |
| Reference no.3 | Name Designation Organization Contact Information – Address; Phone; Email; etc. |  |  |
| Declaration: I confirm my intention to serve in the stated position and present availability to serve for the term of the proposed grant agreement. I also understand that any wilful misstatement described above may lead to my disqualification, before or during my engagement. ___________________________________________ _____________________ Signature of the Nominated Team Leader/Member Date Signed |  |  |  |

SECTION 5: PROPOSED BUDGET ALLOCATION

Please provide budget allocation in the following suggested or similar format:

- Summary of costs

| Level of effort |  | # Days | Cost | Total |
| --- | --- | --- | --- | --- |
|  | Team member #1 | .. days |  |  |
|  | Team member #2 | .. days |  |  |
|  | ….. | .. days |  |  |
|  |  |  | Sub-Total LOE | USD … |
| Travel/mission/other budget |  |  | Cost | Total |
|  | Travel |  |  |  |
|  | Equipment / Technology |  |  |  |
|  | Consultants / sub-grantees |  |  |  |
|  | Other (describe) |  |  |  |
|  |  |  | Sub-Total Travel |  |
|  |  |  | Total | USD … |

ANNEX 2: SAMPLE OF UNCDF LANGUAGE REGARDING PROPRIETARY RIGHTS OF KNOWELDGE PRODUCTS PRODUCED UNDER THIS ASSIGNMENT

6.0	COPYRIGHT, PATENTS AND OTHER PROPRIETARY RIGHTS:

6.1	Except as is otherwise expressly provided in writing in the Agreement, the UNCDF shall be entitled to all intellectual property and other proprietary rights including, but not limited to, patents, copyrights, and trademarks, with regard to products, processes, inventions, ideas, know-how, or documents and other materials which the Recipient Institution has developed for the UNCDF under the Agreement and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Agreement, and the Recipient Institution acknowledges and agrees that such products, documents and other materials constitute works made for the UNCDF. In line with the public good nature of the grant, UNCDF will place all the deliverables specified in the public domain with the intent that they can and should be freely and widely used by other parties and the Recipient Institution shall not be excluded from the ability to use such deliverables on the same basis as other external parties.

6.2	To the extent that any such intellectual property or other proprietary rights consist of any intellectual property or other proprietary rights of the Recipient Institution: (i) that pre-existed the performance by the Recipient Institution of its obligations under the Agreement, or (ii) that the Recipient Institution may develop or acquire, or may have developed or acquired, independently of the performance of its obligations under the Agreement, the UNCDF does not and shall not claim any ownership interest thereto, and the Recipient Institution grants to the UNCDF a perpetual license to use such intellectual property or other proprietary right solely for the purposes of and in accordance with the requirements of the Agreement.

6.3	At the request of the UNCDF; the Recipient Institution shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring or licensing them to the UNCDF in compliance with the requirements of the applicable law and of the Agreement.

6.4	Subject to the foregoing provisions, all maps, drawings, photographs, mosaics, plans, reports, estimates, recommendations, documents, and all other data compiled by or received by the Recipient Institution under the Agreement shall be the property of the UNCDF, shall be made available for use or inspection by the UNCDF at reasonable times and in reasonable places, shall be treated as confidential, and shall be delivered only to UNCDF authorized officials on completion of work under the Agreement.