UNITED NATIONS CAPITAL DEVELOPMENT FUND (UNCDF)

Selecting an Innovation Hub  – to implement an Innovation challenge and Accelerator programme for Uganda

REQUEST FOR APPLICATIONS

Deadline for submission:  15th October 2018

- INTRODUCTION TO THIS REQUEST FOR APPLICATIONS

UNCDF is looking for an innovation hub that can deliver its first cohort of innovation challenge and accelerator model in Uganda. The first cohort will be specific to the agriculture sector.

UNCDF has been using a market development approach to bring digital finance to last-mile customers, especially in rural areas of Uganda. Together with different public and private players, UNCDF has worked to grow digital payments ecosystem and incubate different digital use cases that drive the adoption and usage of digital finance (DF). The primary focus of UNCDF has been linking digital finance to agriculture, by digitizing payments in agriculture value chains. Moreover, UNCDF has worked with private actors to expand the network connectivity and distribution points for digital financial services (DFS).

Whereas significant progress has been made in the number of people owning a bank account or mobile wallet, usage remains low. We’ve learned that DFS uptake will increase as long as value proposition of DFS solution will provide relevant DFS cases. The least active users of digital finance are some of the largest demographic groups:  women, youth, rural families and micro and small enterprises. There is therefore the need to develop more innovations to increase the usage of DFS.

As part of its new strategy in Uganda, UNCDF goal is to empower vulnerable people (farmers, youth, women, refugees and migrants and small entrepreneurs) to lead productive and healthy lives by leveraging innovation and technology in various aspects of their life (finance, agriculture, education, health, water & sanitation, energy, transport).

Mobile devices have become the platform of choice for creating, distributing and consuming innovative digital solutions and services in Africa and Uganda. UNCDF believes that the relevance of digital innovation could significantly grow with the launch of other value-added services and if start-ups are enabled to develop solutions that might solve the pressing needs of low-income population.

To enact the full potential of the start-up ecosystem, there is need for collaboration among various players to ensure that new mobile-based solutions are developed, and can achieve scale and sustainability. UNCDF would like, through its incubator model, to be able to support the start-up ecosystem in Uganda, by supporting the development and scale-up of innovative solutions tackling specific challenges in various sectors.

UNCDF is looking for an Innovation hub, as a partner in implementing the first cohort of its innovation challenge and set-up an incubator model, which will be focusing on innovative digital solutions in the agriculture sector.

The selected innovation hub will be responsible to conduct the following activities, in close coordination with UNCDF.

- Defining and launch the challenge

- Put in place a bootcamp (ideation and prototyping)

- Acceleration that will include in house mentorship and field validation

- Supporting the start-ups across the piloting

The result of this project will be the acceleration of new SMEs/start-ups that will bring in innovative services to Uganda and other UNCDF markets and they will give impetus to the digital economy, thus creating jobs and driving growth. UNCDF will support the incubation/acceleration process of new ideas or existing solutions. Participating start-ups in will receive different types of support as listed below.

- Mentoring: opportunity to work alongside industry / sector leaders so as to provide relevant solutions to current sector challenges;

- Access to infrastructure, collaboration tools and digital platforms;

- Knowledge sharing that includes access to know-how within global and local tech community members and start-up founders;

- Seed capital to fund early-stage piloting of the digital innovations.

The selected start-ups will also have the privilege to get support from UNCDF’s partners both on the technical side (e.g Access to API’s) and on the subject matter side (Agriculture sector partners)

The overall duration of the engagement is expected to take up to 8 months.

  - Purpose of the RFA

UNCDF is promoting digital innovations anchored through an in-country hub that serves as incubator and accelerator of meaningful digital solutions for different sectors and segments especially low-income customers.

As part of this accelerator model, UNCDF is preparing to announce the first cohort in 2018 that would focus on inviting pre-seed stage or legally established start-ups with minimum viable product (MVP) that address specific challenges in the agriculture sector where digital is a key anchor. Funding for the first cohort would come from UNCDF.

The purpose of this request for applications (RFA) is to engage the services of an innovation hub engaged in the space of digital innovation This RFA will result in selecting one potential hub with whom UNCDF will work to launch and to provide guidance and manage the first cohort of UNCDF’s accelerator model in Uganda.

UNCDF will provide a grant and sign a performance-based agreement with the selected hub to manage the entire project and deliver as per the scope of work detailed below.

All applicants should give full consideration to the Principals of Digital Development.

  - Timing

Applications & RFA Calendar:

- Publication date: 1st October 2018

- Deadline for questions in writing 07th October 2018

- Publication answers by UNCDF: 09th October 2018

- Final deadline for applications 15th October 2018 6pm GMT

You may send questions to mm4p@uncdf.org A FAQ document will be generated based on enquiries received on or before 7th of October 2018. The FAQs will be posted on the UNCDF website no later Monday the 09th of October.

Applications should be sent to UNCDF by email at mm4p@uncdf.org no later than midnight 15th October 2018 6pm GMT. Applications should follow the submission format in Annex I.

UNCDF would like to conclude all agreements no later than 2nd week of November.

Activities are expected to start at the 1st week of December 2018. The expected date of full completion of project is 31st July 2019.

  - Contact

Applications and any consultation about this RFA should be submitted via email at mm4p@uncdf.org

  - Responses

- ORGANIZATION CONTEXT AND BACKGROUND INFORMATION

  - Organization Context

The UN Capital Development Fund (UNCDF) makes public and private finance work for the poor in the world’s 47 least developed countries. With its capital mandate and instruments, UNCDF offers “last mile” finance models that unlock public and private resources, especially at the domestic level, to reduce poverty and support local economic development. UNCDF’s financing models work through two channels: financial inclusion that expands the opportunities for individuals, households, and small businesses to participate in the local economy, providing them with the tools they need to climb out of poverty and manage their financial lives; and by showing how localized investments—through fiscal decentralization, innovative municipal finance, and structured project  finance—can drive public and private funding that underpins local economic expansion and sustainable development. By strengthening how finance works for poor people at the household, small enterprise, and local infrastructure levels, UNCDF contributes to SDG 1 on eradicating poverty and SDG 17 on the means of implementation. By identifying those market segments where innovative financing models can have transformational impact in helping to reach the last mile and address exclusion and inequalities of access, UNCDF contributes to a number of different SDGs.

  - Background Information about UNCDF and Digital Finance

UNCDF manages a number of digital financial (DF) initiatives to address the challenges of implementing branchless banking and mobile money in least developed countries (LDCs) in Africa and Asia, as well as in emerging markets and middle-income countries. UNCDF’s long-term mission is to help low-income and rural households in LDCs to enhance their financial security through appropriate, affordable and secure means to receive, manage and save money through “digital financial services” (DFS). UNCDF goal is to help build inclusive digital financial sectors to assure that DFS are provided responsibly, at reasonable cost, by sustainable institutions in a well-regulated environment.

UNCDF pursues a market development approach to digital finance. UNCDF characterizes the evolution of the market as occurring in four phases: Inception, Start-Up, Expansion and Consolidation. To summarize, Inception is when a market has only a few actors with limited outreach that are working without clear policies or supporting DFS infrastructure. In contrast, Consolidation is when a market has a range of competitive actors and services that are clearly regulated and interconnected. Expansion is the critical phase when several players are gaining scale, reaching sustainability and increasing investment.

UNCDF has been using a range of interventions to move the DFS market through the different phases, by providing policy advice, technical support, training and financing.

- SCOPE OF WORK

The selected applicant is expected to support the operations and management of the project activities following UNCDF’s incubation model.

| Activity | Deliverables | Estimated Timelines |
| --- | --- | --- |
| Work with the UNCDF team to define the kick off stage of the accelerator programme - Framing the challenges in the Agricultural sector - Framing the eligibility criteria - Sending out call for applications for innovation - Preliminary selection - Prepare and host an info session to the selected applicants - Prepare and host a Launch event | - Final Project work Plan - Call for application is published - At least 30 startups are selected to be part of the innovation challenge [list & profile of the 30 teams] - Info session attended and delivered successfully - Launch event attended and organized successfully | Dec. 2018 |
| Work with UNCDF to implement a bootcamp [ideation & prototyping] - Prepare and host a 3-day bootcamp - Support the screening and selection process of best innovations - Document key strengths and weaknesses of the emerging teams / solutions | - Boot camp is successfully hosted and implemented. - At least 10 promising prototypes are selected - A profile report of the selected teams and their solutions, including their strengths and weaknesses that need to be addressed in the accelerator | Dec 2018 |
| Work with UNCDF to facilitate and a 3 months acceleration program Implement an in-house mentorship program Facilitate field immersion sessions for testing /iteration / validation of the prototypes (with support from UNCDF field partners) Select most promising minimum viable products that are ready for piloting | - Host and deliver a 3-month in-house acceleration (mentorship) program, customized to the needs of the teams and solutions being accelerated - Organize and facilitate a 1 week field immersion session - innovators going to the field to better understand the context and target market / customer - Organize a final selection process for the selection of 3 best solutions that can be piloted - Deliver a report on the acceleration phase together with a profile of final 3 teams and their solutions. | Jan – March 2019 |
| Work with UNCDF to support a 3 months pilot phase | - Manage the 3 selected teams (and the grant to the teams) during the pilot phase. - Project management (working with stakeholders, keeping schedules and budgets) | April – July 2019 |

The applicants are invited to submit a budget clearly outlining the costs for the implementation of the above activities and deliverables.

- PARAMETERS OF THE AGREEMENT

Outputs and deliverables

The written outputs and deliverables of the work are considered a public good unless otherwise agreed. Thus, all the outputs and deliverables will be placed in the public domain with the intent that they can and should be freely and widely used by other parties.

Agreement

The technical partner is expected to sign a Performance Based Financing (Grant) Agreement with UNCDF (see Annex 2 for a sample of our legal language in this regard).

Language

The deliverables, as well as any and all related correspondence exchanged by the organization and UNCDF, shall be written in English.

- Eligibility criteria and APPLICATION REQUIREMENTS

  - Eligibility requirements

- Applicant(s) should be duly registered in Uganda;

- Not to be in a state of repair or to have been the subject of bankruptcy, liquidation, judicial settlement, safeguarding, cessation of activity or any other similar situation resulting from a similar procedure;

- Not to be included in the United Nations financial sanctions lists, particularly in the fight against the financing of terrorism and against attacks on international peace and security;

- To have fulfilled obligations relating to the payment of social security contributions or obligations relating to the payment of taxes according to the legal provisions in its country of incorporation;

  - Minimum qualification criteria

- Experience of person(s) managing the selected firm would be crucial. The persons engaged should have a background in space of digital innovation.

- Successfully conducted similar assignments at a country or regional level either in individual capacity or as a firm with proven excellent results.

- The technical proposal should clearly present:

  - The hub’s acceleration methodology and process for start-ups

  - An outline of the curriculum (content) that the hub uses to mentor start-ups

  - A list of mentors with their CV’s associated with the hub

- Ability to work in the language of the country / ies proposed (i.e. English)

- Submit a complete application

  - Structure of the Application

- The application includes a suggested template for submissions in Annex 1: Submission Format.  Section 1 must be followed as in the Annex.  Applications may choose a format for sections 2, 3 and 4 provided all the necessary information is included.

- Additional documents or links to documents may be included at the applicant’s discretion.

  - Submission of the Application

- Applications and any consultation about this RFA should be submitted via email at mm4p@uncdf.org

- The subject line of the email should be:  RFA:  Innovation Hub – Uganda

- The deadline to submit the applications is 20th October 2018 6pm midnight Greenwich Mean Time

- EVALUATION CRITERIA

The evaluation will follow the combined scoring method:

Rating the Technical Proposal (TP):

TP Rating = (Total Score Obtained by the Offer / Max. Obtainable Score for TP) x 100

Rating the Financial Proposal (FP):

FP Rating = (Lowest Priced Offer / Price of the Offer Being Reviewed) x 100

Total Combined Score:

(TP Rating) x (Weight of TP, e.g. 70%)

+ (FP Rating) x (Weight of FP, e.g., 30%)

Total Combined and Final Rating of the Proposal

Technical proposal (including CVs of team): 700 Points

Expertise of the Firm; Points Obtainable. Expertise of the firm in the digital innovation space and running accelerator programs. Experience working with start-ups/entrepreneurs with focus on financial inclusion and low-income segments with be of added advantage; 150. Quality of the acceleration curriculum content and team of mentors; 150. Quality assurance procedures and mechanism, guarantee provided by the individual in lead or firm; 100. Total Part 1; 400. Understanding of the mandate and proposed approach; Points Obtainable. The proposal addresses the requirements laid out in the Scope of Work section appropriately; 100. The design of the proposed approach is structured, and appropriate to UNCDF requirements and to achieve the gaols; 100. The proposal presents efficient and cost-effective measures ways to manage the implementation; 100. Total Part 2; 300.

Financial Proposal (300 points)

Only the financial offers of the applicant scoring at least 70% of the technical proposal will be

To be computed as a ratio of the Proposal’s offer to the lowest price among the proposals received by UNCDF. Total 1,000 points.

ANNEX 1: SUBMISSION FORMAT

[insert: Location]

[insert: Date

To:	Carlos Escrivá Gil, Operations Analyst, and MM4P

Dear Sir

We, the undersigned, hereby apply for Innovation Hub  in accordance with your Request for Application dated [insert: Date] and our Application.  We are hereby submitting our Application, which includes the Technical Proposal including proposed budget allocation.

We hereby declare that:

- All the information and statements made in this Application are true and we accept that any misrepresentation contained in it may lead to our disqualification; and

- We have no outstanding bankruptcy or pending litigation or any legal action that could impair our operation as a going concern

We confirm that we have read, understood and hereby accept the duties and responsibilities required of us in this RFA, and the standard language of UNCDF’s Performance Based Agreements (PBA), including the requirements regarding the public good nature of the outputs to be produced (see Annex 2 for a sample of our legal language in this regard.

We fully understand and recognize that UNCDF is not bound to accept this application that we shall bear all costs associated with its preparation and submission, and that UNCDF will in no case be responsible or liable for those costs, regardless of the conduct or outcome of the evaluation.

We remain,

Yours sincerely,

Authorized Signature [In full and initials]:

Name and Title of Signatory:

Name of Firm:

Contact Details:

[Please mark this letter with your corporate seal, if available]

Page ________of ________ pages

SECTION 1: GENERAL APPLICANT’S INFORMATION

- Applicant’s Legal Name:

- Type of Organization (e.g. commercial for profit firm, educational, non-profit, etc.):

- In case of Joint Venture (JV), legal name of each party:

- Actual or intended Country/ies of Registration/Operation:

- Year of Registration:

- Countries of Operation / No. of staff in each Country / Years of Operation in each Country

- Legal Address/es in Country/ies of Registration/Operation

- Description and value of top three grants or contracts relevant to the scope of this RFA for the past five years. Provide the following information for each of them.

- Name of the project (website if applicable):

- Date, location:

- Client/Funder (if applicable):

- Grant/Contract value in USD:

- Types of results produced/activities undertaken:

- References, contact details (name, position, email, phone number):

- Applicant’s Authorized Representative Information

- Name:

- Address:

- Telephone/Fax numbers:

- Email Address:

- Are you in the UN Ineligibility List?  ☐ YES or ☐ NO

- Attached are copies of original documents of:

☐ Financial statements for the past 2 years (in English or French)

☐Letter from the applicant organization’s executive director, CEO, or board, expressing its commitment to the execution and participation in this process

☐Complete resumes of all the team members involved in the assignment

☐ Staff time allocation spreadsheet per result

☐Electronic copies and hyperlinks where available of studies, knowledge products produced under similar assignments and list of dissemination channels

SECTION 2: SPECIFIC EXPERIENCE FOR THE ASSIGNMENT

- Please describe your organization’s experience in producing similar projects. For each one, make sure you describe the following (maximum 1 page per project up to 5 projects):

- Name of the project (website if applicable);

- Client/Funder (if applicable);

- Grant/Contract value;

- Description of the approach/methodology;

- Types of outputs/deliverables produced and activities undertaken;

- Tools used or developed (dashboards, maps, etc.);

- Results of project for client, if known;

- Time it took you to complete the assignment, dates, location;

- Number of people and names of the staff that participated in the assignment;

- Knowledge product production and dissemination strategy of the assignment;

- References, contact details (name, position, phone number, email);

- The applicant should describe your organization’s expertise in managing incubator or accelerator programme and the key insights, lessons learned or other takeaways from this work not mentioned in no. 12 above. (maximum 3 pages)

  - The applicant should describe their specific experience related to managing the challenge windows and methodology deployed around accelerator programme, providing more in depth explanation on specific tools with an emphasis on their relevance, accessibility and use by participants

  - Experience in the relevant country/ies

- The applicant shall clearly state the tools and content that they intend to bring in terms of methodology to support the process from design to prototyping   (maximum 1 page)

- The applicant should describe the team, knowledge product production, packaging and dissemination process of your organization (maximum 2 page)

- The applicant should note their organization policies around legal and ethical use of methodology or content or data and provide copies or links, if available.

SECTION 3: APPROACH AND IMPLEMENTATION PLAN (max 5 pages)

- Approach to Scope of Work and Proposed Deliverables

The applicants should propose a scope of work.  As noted the applicant may suggest an alternative scope of work and / or deliverables that achieves the same objectives.  However, the applicant should address each component of the SOW in Section 3 of the RFA, even if they are proposing to do very little in that component.

Highlight the type of support or guidance you would need from UNCDF.

- Describe the proposed tools 
The applicant should describe the tools and may provide links to prototypes or similar tools for review. Indicate if these will be newly developed or adapted from existing tools; on-going support provided or needed for maintenance or adaptation; user-friendliness; plan to make some or all accessible beyond the applicant and UNCDF.

- Approach to the Implementation and working with the MM4P Team

The applicant should provide a detailed description of how the applicant will plan, implement and deliver the overall project. Indicate the type of team, resources that the applicant will provide, how it will organize itself for the work.  Pay specific attention to the appropriateness to local conditions and project environment.  Highlight the support it would need from UNCDF.

- Approach to Communications

The applicant should provide detail on what type of knowledge products from deliverables and how it prefers to communicate the progress and results on the overall project as noted in section 3.3 of the RFA. Also note what support would be needed from UNCDF.

- Approach to legal compliance, data privacy and security, and ethical use of data

The applicant should clear state how it will protect customer data privacy and security and the extent to which the proposed project will comply with of the Principles of Digital Development.  For principles that cannot be upheld in the project, the applicant should clearly state the reasons.  The applicant should note how it intends to ensure that its work is in compliance with local laws and regulations.

- Implementation Timelines

The applicant shall submit a Gantt Chart or Project Schedule indicating the detailed sequence of phases, activities that will be undertaken and their corresponding timing, specifying timelines, responsibility, and time devoted to each result.  Start date should be no sooner than 15 March 2016.

- Risks / Mitigation Measures

Please describe the potential risks for the implementation of this project that may impact achievement and timely completion of expected results as well as their quality.  Describe measures that will be put in place to mitigate these risks. The applicant should address issues around data privacy and security.

- Technical Quality Assurance Review Mechanisms

The methodology shall also include details of the applicant’s internal technical and quality assurance review mechanisms.

SECTION 4: PERSONNEL

- Management Structure

Describe the overall management approach toward planning and implementing this result.  Include an organization chart for the management of the project describing the relationship, roles and responsibilities of key positions and designations.

- Sub-grantees, contractors or other critical relationships

Explain whether any work would be delegated, to whom, how much percentage of the work, the rationale for such, and the roles of the proposed sub-grantees or contractors.  Special attention should be given to providing a clear picture of the role of each entity and how everyone will function as a team. If there are any other critical relationships or partnerships, please highlight them here.  For other organizations that play a substantial role (e.g.  > 25% of time or cost), please provide items 1 thru 8 in Section 1of this Annex.

- Staff Time Allocation

Provide a spreadsheet to show the activities of each staff member and the time allocated for his/her involvement.  Please describe any travel/missions/field visits planned for this assignment indicating team member participation and duration.

(Note: Substitution of key personnel will once the grant has been awarded will be subject to the written approval of UNCDF.  No increase in grant will be considered as a result of any substitution.)

- Qualifications of Key Personnel

Provide the CVs for key personnel (Team Leader, Managerial, Technical experts) that will be provided to support the implementation of this project. CVs should demonstrate qualifications in areas relevant to the results to be produced.

In addition to the CVs, please submit a summary for each person in the following format:

| Name: |  |  |  |
| --- | --- | --- | --- |
| Position for this Contract: |  |  |  |
| Nationality: |  |  |  |
| Contact information: |  |  |  |
| Countries of Work Experience: |  |  |  |
| Language Skills: |  |  |  |
| Educational and other Qualifications: |  |  |  |
| Summary of Experience: Highlight experience in the region and on similar projects. |  |  |  |
| Relevant Experience (From most recent): |  |  |  |
| Period: From – To | Name of Organization/Project/Activity, if applicable: |  | Job Title and Activities undertaken/Description of actual role performed: |
| e.g. June 2015-January 2016 |  |  |  |
| Etc. |  |  |  |
| Etc. |  |  |  |
| References no.1 (minimum of 3): | Name Designation Organization Contact Information – Address; Phone; Email; etc. |  |  |
| Reference no.2 | Name Designation Organization Contact Information – Address; Phone; Email; etc. |  |  |
| Reference no.3 | Name Designation Organization Contact Information – Address; Phone; Email; etc. |  |  |
| Declaration: I confirm my intention to serve in the stated position and present availability to serve for the term of the proposed grant agreement. I also understand that any wilful misstatement described above may lead to my disqualification, before or during my engagement. ___________________________________________ _____________________ Signature of the Nominated Team Leader/Member Date Signed |  |  |  |

SECTION 5: PROPOSED BUDGET ALLOCATION

Please provide budget allocation in the following suggested or similar format:

- Summary of costs

| Level of effort |  | # Days | Cost | Total |
| --- | --- | --- | --- | --- |
|  | Team member #1 | .. days |  |  |
|  | Team member #2 | .. days |  |  |
|  | ….. | .. days |  |  |
|  |  |  | Sub-Total LOE | USD … |
| Travel/mission/other budget |  |  | Cost | Total |
|  | Travel |  |  |  |
|  | Equipment / Technology |  |  |  |
|  | Consultants / sub-grantees |  |  |  |
|  | Other (describe) |  |  |  |
|  |  |  | Sub-Total Travel |  |
|  |  |  | Total | USD … |

ANNEX 2: SAMPLE OF UNCDF LANGUAGE REGARDING PROPRIETARY RIGHTS OF KNOWELDGE PRODUCTS PRODUCED UNDER THIS ASSIGNMENT

6.0	COPYRIGHT, PATENTS AND OTHER PROPRIETARY RIGHTS:

6.1	Except as is otherwise expressly provided in writing in the Agreement, the UNCDF shall be entitled to all intellectual property and other proprietary rights including, but not limited to, patents, copyrights, and trademarks, with regard to products, processes, inventions, ideas, know-how, or documents and other materials which the Recipient Institution has developed for the UNCDF under the Agreement and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Agreement, and the Recipient Institution acknowledges and agrees that such products, documents and other materials constitute works made for the UNCDF. In line with the public good nature of the grant, UNCDF will place all the deliverables specified in the public domain with the intent that they can and should be freely and widely used by other parties and the Recipient Institution shall not be excluded from the ability to use such deliverables on the same basis as other external parties.

6.2	To the extent that any such intellectual property or other proprietary rights consist of any intellectual property or other proprietary rights of the Recipient Institution: (i) that pre-existed the performance by the Recipient Institution of its obligations under the Agreement, or (ii) that the Recipient Institution may develop or acquire, or may have developed or acquired, independently of the performance of its obligations under the Agreement, the UNCDF does not and shall not claim any ownership interest thereto, and the Recipient Institution grants to the UNCDF a perpetual license to use such intellectual property or other proprietary right solely for the purposes of and in accordance with the requirements of the Agreement.

6.3	At the request of the UNCDF; the Recipient Institution shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring or licensing them to the UNCDF in compliance with the requirements of the applicable law and of the Agreement.

6.4	Subject to the foregoing provisions, all maps, drawings, photographs, mosaics, plans, reports, estimates, recommendations, documents, and all other data compiled by or received by the Recipient Institution under the Agreement shall be the property of the UNCDF, shall be made available for use or inspection by the UNCDF at reasonable times and in reasonable places, shall be treated as confidential, and shall be delivered only to UNCDF authorized officials on completion of work under the Agreement.